## Schedule
GAME STUDIO |  | August 23 | May 4 | May 11 | August 30 | May 24 | September 6 | September 13 | September 20 | September 27 | October 4 | October 11 | October 18 | October 25 | November 1st | 2026-11-08 | November 15 | November 22 | November 29 | December 6 | December 13
|  | PRE PRODUCTION | [9 empty] | ALPHA PHASE | [8 empty] | Beta
[9 empty] | Pitch Day! |  | Design Pillars | Dev Begins |  |  | Playtest |  | Playtest |  |  | Alpha Ends
Track / Focus | Name | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20
Art | Ava | Week 1: Ideation & Gen. Plan; Design Pillars Week 10: Desert Level 3D Boss Concept; Dev Begins Week 11: Fall Break!; Dev Begins Week 12: Boss Textures
Art | Ben | Week 1: Ideation & Gen. Plan; Design Pillars Week 10: More VFX Foam; Dev Begins Week 12: Foam Shader Polish
Tech Art | Cam | Week 1: Ideation & Gen. Plan; Design Pillars Week 10: Desert Level Region Mockup; Dev Begins Week 13: Rigging Pass
Design | Dee | Week 1: Ideation & Gen. Plan; Design Pillars Week 10: Desert Levels Blueprint Iteration; Dev Begins Week 12: Playtest Plan
Engineering | Eli | Week 1: Ideation & Gen. Plan; Design Pillars Week 10: Desert Final Level Boss Fight; Dev Begins Week 12: Enemy AI Pass
Production | Fay | Week 1: Ideation & Gen. Plan; Design Pillars Week 10: Presentation, Timeline, and Task updates; Dev Begins Week 12: Sprint Review