## Sheet1
Milestone | Start Date | End Date | Owner | Status | Phase | Notes
Kickoff meeting | 2026-09-28 |  | Alex | Done | Planning
Requirements sign-off | 2026-10-02 |  | Priya | In progress | Planning | Waiting on legal review
Design sprint | 2026-10-05 | 2026-10-16 | Sam | In progress | Design
Prototype demo | 2026-10-09 |  | Sam | Not started | Design | Demo to stakeholders on Zoom
Beta build freeze | 2026-10-13 |  | Jordan | Not started | Build
Marketing brief due | 2026-10-19 |  | Lee | Not started | Launch
User testing round 1 | 2026-10-26 | 2026-10-30 | Priya | Not started | Testing
Public launch | 2026-11-16 |  | Everyone | Not started | Launch | 🚀